## Sheet1
Week | <component> | Goals | Effort | Difficulty
2023-04-03 | setup projectplan and repos | All tools and plans are setup | 20h | medium
2023-04-10 | Setup CI environment and Pipeline | CI Integration is setup and works | 40h | high
2023-04-17 | Setup Continour Delivery Pipeline and test | CD Pipeline is setup and works | 40h | high
2023-04-24 | Skleran can be used |  | 5h | medium
2023-05-01 | Documentation | readme file is completed, Screenscast ist created. | 20h | medium
2023-05-08
2023-05-15
2023-05-22
2023-05-29
2023-06-05
2023-06-12
2023-06-19
| Goals | Goals
Formulas:
Week = [Week, row above]+7